## Sheet1
| Week 1 | 2020-10-09 | Week 2 | 2020-10-16 | Week 3 | 2020-10-23 | Week 4 | 2020-10-30 | Week 5 | 2020-11-06 | Week 6 | 2020-11-13 | Week 7 | 2020-11-20 | Week 8 | 2020-11-27
Milestones |  | Sprint | zero |  |  | Sprint | one |  |  | Sprint | two |  |  | Sprint | three
|  |  | Stand up meeting 1 |  |  |  | Stand up meeting 2 |  |  |  | Stand up meeting 3 |  |  |  | Stand up meeting 4
|  | Planning |  |  | User story: I wish to create a molecule |  |  |  | User story: I wish to predict a shape |  |  |  | User story: I wish to use a different EA.
Plan |  | Setup | [7 empty] | Update risk assessment for COVID |  |  | Try an EA which alters one atom at a time.
|  | Literature review | [6 empty] | Try an EA which makes many molecules and compares them.
Test |  | Target user questionnaires | [7 empty] | See if the EA works to decrease energy |  |  | Try to get a better structure prediction than before.
[9 empty] | See if the molecule's shape is displayed in the cell properly |  |  |  | Test num iterations, E calcs, array changes.
[6 empty] | Allow user to select elements |  |  |  | Make the EA |  |  |  | Make the EA.
Application | [5 empty] | Create a logo |  |  |  | Improve exception handling |  |  | Try without crossover and remove all parents.
[6 empty] | Create UI |  |  |  | Choose EA parameters |  |  | Move from test area to application.
[6 empty] | XML |  |  |  | Create models of the molecule
Display the molecular formula
| Week 9 | 2020-12-04 | Week 10 | 2020-12-11 | Week 11 | 2020-12-18 | Christmas holiday |  | Week 12 | 2021-01-15 | Week 13 | 2021-01-22 | Week 14 | 2021-01-29
Milestones |  | Sprint | four |  | Sprint | five | Christmas holiday |  | Sprint | five |  | Sprint | six
Christmas holiday
| User story: I wish to view molecule, info & PES |  |  |  | Testing |  | Christmas holiday |  | Testing |  | User story: I wish to interact with the algorithm
Plan |  |  |  |  | Feedback & changes |  | Christmas holiday |  | Feedback & changes
[5 empty] | Fixes & improvements |  | Christmas holiday |  | Fixes & improvements
Test |  |  |  |  | Usability tests |  | Christmas holiday |  | Usability tests
Christmas holiday
Christmas holiday
Application | [6 empty] | Christmas holiday
Christmas holiday
Christmas holiday
Christmas holiday
| Week 15 | 2021-02-05 | Week 16 | 2021-02-12 | Week 17 | 2021-02-19 | Week 18 | 2021-02-26 | Week 19 | 2021-03-05 | Week 20 | 2021-03-12
Milestones |  | Sprint | seven |  |  | Sprint | eight |  |  | Sprint | nine
[7 empty] | Finish code |  |  |  | Submit showcase materials!
|  | Testing |  |  |  | Final fixes & clean up |  |  |  | Showcase materials
Plan |  | Feedback & changes |  |  |  | Start writing report
Test |  | Usability tests
Application
| Week 21 | 2021-03-19 | Week 22 | 2021-03-26 | Easter holiday |  | Week 23 | 2021-04-23 | Week 24 | 2021-04-30 | Week 25 | 2021-05-07 | Week 26 | 2021-05-14
Milestones |  |  |  |  | Easter holiday
[5 empty] | Easter holiday | [7 empty] | Submit final report!
Easter holiday
Plan |  |  |  |  | Easter holiday
Easter holiday
Test |  |  |  |  | Easter holiday
Easter holiday
Easter holiday
Application |  |  |  |  | Easter holiday
Easter holiday
Easter holiday
Easter holiday